## Sheet1
Date | 2013-07-15 | 2013-07-16 | 2013-07-17 | 2013-07-18 | 2013-07-19 | 2013-07-22 | 2013-07-23 | 2013-07-24 | 2013-07-25 | 2013-07-26 | 2013-07-29 | 2013-07-30 | 2013-07-31 | 2013-08-01 | 2013-08-02 | 2013-08-03
Remaining hours | 135 | 123 | 107 | 87 | 63 | 62 | 61 | 60 | 59 | 58 | 57 | 56 | 40 | 16 | 8 | 0
Actual Remaning | 111 | 99 | 94
% Complete | 25% |  |  | 25% | [8 empty] | 100% | 75%
Subject (Tasks) | Populate Pattern List Workbook (list of all patterns needed and priorities) and review | Run patterns for each test mode to ensure that sim environment works correctly for all modes | Set up pattern conversion flow and validate for each test mode | Set up pattern resim flow and validate for each test mode | Set up regression flow | Receive and/or develop all pattern source files | Simulate, convert and RTL resim all patterns | Populate GLS testbench from Verification engineer and run sanity patterns to ensure env is working correctly | GLS Resim all patterns requiring gate level resim | Set up PRESO environment | Generate RAMBIST patterns | Resim patterns | DRT documentation and review | Test Plans | Probe and test hardware requirements, schematics and layout review | Build test program; develop Visual Basic code as needed
Start Date | 2013-07-11 | 2013-07-14 | 2013-07-17 | 2013-07-20 | 2013-07-23 | 2013-07-26 | 2013-07-29 | 2013-08-01 | 2013-08-04 | 2013-08-07 | 2013-08-10 | 2013-08-13 | 2013-08-16 | 2013-08-19 | 2013-08-22 | 2013-08-25
Due Date | 2013-07-19 | 2013-07-26 | 2013-08-02 | 2013-08-09 | 2013-08-16 | 2013-07-27 | 2013-07-30 | 2013-08-02 | 2013-08-05 | 2013-08-08 | 2013-08-11 | 2013-08-14 | 2013-09-01 | 2013-09-12 | 2013-08-30 | 2013-09-02
Planned hours Total Work | 8 | 12 | 16 | 20 | 24 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 16 | 24 | 8 | 8
owner | Bruce Robertson | Bruce Robertson | Bruce Robertson | Bruce Robertson | Bruce Robertson | Bruce Robertson | Bruce Robertson | Bruce Robertson | Bruce Robertson | Bruce Robertson | Bruce Robertson | Bruce Robertson | Bruce Robertson | Bruce Robertson | Bruce Robertson | Bruce Robertson