## test case Burn_down_tasks (2)
Date | Remaining hours | Actual Remaning | % Complete | Subject (Tasks) | Start Date | Due Date | Planned hours Total Work | owner | Actual Work | Reminder Time | Date Completed | Billing Information | Categories | Companies | Contacts | Mileage | Notes | Priority | Private | Role | Schedule+ Priority | Sensitivity | Status
2013-07-15 | 135 | 111 | 25% | Populate Pattern List Workbook (list of all patterns needed and priorities) and review | 2013-07-11 | 2013-07-19 | 8 | Bruce Robertson | [6 empty] | Bruce Robertson |  | Bruce to put on shared review | 1 |  |  |  | Normal
2013-07-16 | 123 | 99 |  | Run patterns for each test mode to ensure that sim environment works correctly for all modes | 2013-07-14 | 2013-07-26 | 12 | Bruce Robertson | [9 empty] | 2 |  |  |  | Normal
2013-07-17 | 107 | 94 |  | Set up pattern conversion flow and validate for each test mode | 2013-07-17 | 2013-08-02 | 16 | Bruce Robertson | [9 empty] | 2 |  |  |  | Normal
2013-07-18 | 87 |  | 25% | Set up pattern resim flow and validate for each test mode | 2013-07-20 | 2013-08-09 | 20 | Bruce Robertson | [9 empty] | 2 |  |  |  | Normal
2013-07-19 | 63 |  |  | Set up regression flow | 2013-07-23 | 2013-08-16 | 24 | Bruce Robertson | [9 empty] | 2 |  |  |  | Normal
2013-07-22 | 62 |  |  | Receive and/or develop all pattern source files | 2013-07-26 | 2013-07-27 | 1 | Bruce Robertson | [9 empty] | 1 |  |  |  | Normal
2013-07-23 | 61 |  |  | Simulate, convert and RTL resim all patterns | 2013-07-29 | 2013-07-30 | 1 | Bruce Robertson | [9 empty] | 1 |  |  |  | Normal
2013-07-24 | 60 |  |  | Populate GLS testbench from Verification engineer and run sanity patterns to ensure env is working correctly | 2013-08-01 | 2013-08-02 | 1 | Bruce Robertson | [9 empty] | 1
2013-07-25 | 59 |  |  | GLS Resim all patterns requiring gate level resim | 2013-08-04 | 2013-08-05 | 1 | Bruce Robertson | [9 empty] | 1
2013-07-26 | 58 |  |  | Set up PRESO environment | 2013-08-07 | 2013-08-08 | 1 | Bruce Robertson | [9 empty] | 1
2013-07-29 | 57 |  |  | Generate RAMBIST patterns | 2013-08-10 | 2013-08-11 | 1 | Bruce Robertson | [9 empty] | 3
2013-07-30 | 56 |  |  | Resim patterns | 2013-08-13 | 2013-08-14 | 1 | Bruce Robertson | [9 empty] | 3
2013-07-31 | 40 |  | 100% | DRT documentation and review | 2013-08-16 | 2013-09-01 | 16 | Bruce Robertson | [9 empty] | 3
2013-08-01 | 16 |  | 75% | Test Plans | 2013-08-19 | 2013-09-12 | 24 | Bruce Robertson | [9 empty] | 2
2013-08-02 | 8 |  |  | Probe and test hardware requirements, schematics and layout review | 2013-08-22 | 2013-08-30 | 8 | Bruce Robertson | [9 empty] | 2
2013-08-03 | 0 |  |  | Build test program; develop Visual Basic code as needed | 2013-08-25 | 2013-09-02 | 8 | Bruce Robertson | [9 empty] | 2